## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/14-9/28 | Decided on tech stacks for different team members. Decision to change the database from MongoDB to Mysql. Set roles and responsibilities for the team members. Settled on a group and project name. | MongoDB is not suitable for the project due to safety concerns with monetary transactions | Assigning roles and responsibilities to team members. Deciding on project and group names. Planning for presentations. | At least one meeting per week. A team leader should prepare a basic agenda for the meeting and members should rotate as minutes takers. Change in database choice for better security. | 20 | 12 | 5 | 3 | 2 | 90 | 18 | 5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Bhargav Gundapaneni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 6 | 4 | 2 | 0 - learnt the github Agile 1 - modules required for the project, 5 - communicated through inperson and zoom 6 - set the git & github account | 2 | 2 | 1 |  |  | 1 | 1 | 0.5 | 1. git setup,and commit the message andd connected to VScode 2. Prepapred a slides for the Iteration 0 presentation | unable to decide which database to use regarding functuonal modules have to work on more regarding the functional modules | planned to work on functional modules and work on learning the spring boot and take look on some spring boot projects | 0 - work on slides for presentation 1 - identify requirements work on functional modules | 7
2 | 9/21-9/28 | 10 | 8 | 2 | 0 - Learning about Spring and regarding some implemtation steps 1 - worked on modulees functional 3 - functional modules expected one worked what 5 - communicated through inperson and zoomkind od functions we need 7 - work on slides | 2 | 1 |  | 5 |  | 1 |  | 1 | 1. worked on functional modules slides preparation 3. Presention on functional modules 4. Discussed regarding functional module which one to work on more | 1. need to arrange more inpperson meetings | decided not to work much on implemting the on payments due to payments issues and security and planned accordingly what are rewiref for the project will focus on those modules more instead of focusing on all of them | 0 - have to work on the implemtation and learning spring based projects 3 - work on implemation of dunctional modules accordingly | 14
3 | 9/28-10/5

## Haoran Dai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader & Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 5 | 3 | 2 | 0 - Review the git 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 2 | 1 |  |  | 0.5 | 1 | 0.5 | 1. Write the readme 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Group member not farmiliar with git, and I need to teach him 2. communication is not clear. Task assignments is not clear. | 1. teach Yibo about the git basic operations 2. Ask everyone if they still had any question | 0 - Make the slides for the presentation 1 - continue to define requirements 3 - do some research about the tech stacks | 6
2 | 9/21-9/28 | 10 | 8 | 2 | 0 - Learn about some basic knowledge about Network 1 - define high level requirements 3 - make project slides, send reminders to team members, check the draft for the presentation 6 - set up MongoDB 7 - research similar products, prepare presentation, write the RiskManagement document | 1 | 0.5 |  | 5 |  |  | 1 | 0.5 | 1. Make the slides 2. Organize meetings twice a week to ensure the progress of everyone's work. 3. Participate in Iteration 0 presentation 4. Decide to change the database | 1. Group member are not very concern about the draft for the presentation 2. communication is not clear. Task assignments is not clear. | 1. Everyone is required to write the part they are responsible for. The specific part of the speech can not be written, but others must write it. 2. I will emphasize to everyone at the next in person meeting. | 0 - Learn about Java Web basic 1 - continue to define requirements 3 - do some research about the tech stacks | 16
3 | 9/28-10/5

## Huanzhou Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:Design Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 8 | 6.5 | 1.5 | 0: Initial research on React's capabilities, installing necessary libraries and tools. Dive into MongoDB basics. 1: Preliminary requirement analysis for the project based on the chosen tech stacks. 5: First team meeting to outline project objectives, set up communication channels. 6: Set up the development environment for React and MongoDB. 7: Scour online forums and documentation for potential challenges and pitfalls. | 3 | 2 |  |  |  | 1.5 | 1 | 0.5 | 1. Basic understanding of React and MongoDB. 2. Defined project requirements. 3. Setup of the initial development environment. | 1. Difficulty in understanding certain React functionalities. 2. Setting up MongoDB was more time-consuming than expected. | 1. Focus more on understanding React libraries and components. 2. Schedule a dedicated time to troubleshoot MongoDB setup issues. | 0: Dive deeper into React functionalities. 1: Finalize database schema for MongoDB. 2: Begin design phase for project architecture. | 9
2 | 9/21-9/28 | 10 | 8 | 2 | 0: Advanced React tutorials, understanding state management. 2: Design frontend components using React and outline how MongoDB will serve data. 3: Start implementing basic CRUD operations using MongoDB. 5: Regular check-in meetings, discussing challenges faced. 6: Modify development environment based on project progression. 7: Consult online communities for specific challenges faced during implementation. | 3.5 |  | 3 | 1.5 |  | 1 | 0.5 | 0.5 | 1. Initial frontend components designed. 2. Established connection between React and MongoDB, demonstrating basic data display. 3. Addressed and rectified some of the initial issues from week 1. | 1. Challenges in designing a responsive frontend. 2. Encountered data retrieval issues from MongoDB. | 1. Explore more React libraries for responsive design. 2. Research more on MongoDB best practices for data retrieval. | 2: Continue refining frontend design. 3: Introduce more complex operations using MongoDB. 4: Start testing the current functionalities. | 11

## Qinchen Gu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Q&A Leader & Front-end developer
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 7 | 6 | 1 | 0 - learn git, html, css 1 - define high level requirements 5 - communicate with teammembers, get to know each other 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 |  |  |  | 1 | 1 | 0.5 | 1.Get to know each other 2.Divide the work and take charge of front-end 3.Set up git | 1. Know nothing about html, css, javascript and react 2. Not so good in communication with teammates and not divide roles yet | 1.Start front-end stack tutorials, start from html and css, and finish it in a week | 0 - Continue learning React and JavaScript 5 - Continue communication with teammates about project 7 - prepare presentation | 6
2 | 09/21-09/28 | 8 | 6 | 2 | 0 - learn html, css, JavaScript 5 - communicate about roles, presentation and project needs 7 - prepare presentation | 3 |  |  |  |  | 1 |  | 2 | 1.Decide I should speech about tech stacks 2.Finish part of pre draft, especially for myself and Huanzhou 3.Take charge of Q&A leader | 1. Not got enough knowledge for front-end develop | 1.Continue html, css tutorials and start JavaScript tutorials 2.Finish pre draft and ready for pre | 0 - Continue learning React and JavaScript 5 - Continue communication with teammates about project | 6
3 | 09/28-10/05 | 5.5 | 4.5 | 1 | 0 - learn JavaScript, React 2 - design where to start project and design home page 5 - communicate about project needs and where to start | 3 |  | 1 |  |  | 0.5 |  |  | 1.Finish a part of MeetingMinutes 2.Discuss with teammates about database stack change | 1.Still not got enough knowledge for react 2.Don't know where to start our first page | 1.Finish React tutorial in 2 weeks and know how to build websites 2.start the project making and finish home page | 0 - Continue learning React and JavaScript 3 - finish first page-homepage 5 - Continue communication with teammates about project | 6

## Xiaocheng Kang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement & Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn with teammates about what to do 1 - define what I need to do with project 5 - make project plans 6 - setup git | 2 | 1 |  |  |  | 1 | 1 |  | setup github, doing commiting and lab1 | Forget how to done git firstly, it takes some time to retrive. | Finishing learning how to do git things | 0 - continue lerning what we should do 1 - continue finding which part I need to complete 5 - make more details for project plan | 6
2 | 09/21-09/28 | 8 | 7 | 1 | 0 - learn back what to do a website 1 - Make sure what we want to display, and what others want 5 - Project Plan completed 6 - setup Visual Studio for me to write codes 7 - Prepare the presentation for iteration 0 | 5 | 1 |  |  |  | 0.5 | 0.5 | 1 | 1. Complete the SPPP document 2. Prepare the project 3. Meeting to do the presentation slides 4. Participate in Iteration 0 presentation | 1. Not very sure the SPPP file is a great completion 2. Stuck on which DB we should use | 1. Finishing the tutorial of Web Design, should be able to complete a templete website. 2. Received tasks from team leader, let me know what I should do for next | 0 - learn more about Web Design things 1 - Using learned knowledge to create a web template 2 - Design a templete 4 - Test if the web running correct 5 - meeting to find out if it is possible | 7