## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 |  | Decided on tech stacks for different team members. Decision to change the database from MongoDB to Mysql. Set roles and responsibilities for the team members. Settled on a group and project name. | MongoDB is not suitable for the project due to safety concerns with monetary transactions | Assigning roles and responsibilities to team members. Deciding on project and group names. Planning for presentations. | At least one meeting per week. A team leader should prepare a basic agenda for the meeting and members should rotate as minutes takers. Change in database choice for better security. | 20 | 12 | 5 | 3 | 2 | 20 | 4 | 5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Haoran Dai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader & Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 5 | 3 | 2 | 0 - Review the git 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 2 | 1 |  |  | 0.5 | 1 | 0.5 | 1. Write the readme 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Group member not farmiliar with git, and I need to teach him 2. communication is not clear. Task assignments is not clear. | 1. teach Yibo about the git basic operations 2. Ask everyone if they still had any question | 0 - Make the slides for the presentation 1 - continue to define requirements 3 - do some research about the tech stacks | 6
2 | 9/21-9/28 | 10 | 8 | 2 | 0 - Learn about some basic knowledge about Network 1 - define high level requirements 3 - make project slides, send reminders to team members, check the draft for the presentation 6 - set up MongoDB 7 - research similar products, prepare presentation, write the RiskManagement document | 1 | 0.5 |  | 5 |  |  | 1 | 0.5 | 1. Make the slides 2. Organize meetings twice a week to ensure the progress of everyone's work. 3. Participate in Iteration 0 presentation 4. Decide to change the database | 1. Group member are not very concern about the draft for the presentation 2. communication is not clear. Task assignments is not clear. | 1. Everyone is required to write the part they are responsible for. The specific part of the speech can not be written, but others must write it. 2. I will emphasize to everyone at the next in person meeting. | 0 - Learn about Java Web basic 1 - continue to define requirements 3 - do some research about the tech stacks | 16
3 | 9/28-10/5