## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | one member left our group | 1 | 3 | 4 | 4*2*5=40 | team leader and all members | N/A | Increase the workload of each person. Two people are responsible for front-end development, two people are responsible for back-end development, and one person is responsible for assistance. | No one dropped the class so far | Open
add new team members
Lack of motivation or responsibility
Communication | duplicate work
worked on wrong components
useless work
| inconsistent work | Because someone can't attend the meeting, the message of the meeting will not be clear enough. | 5 | 3 | 1 | 4*2*4=32 | team leader | 2023-10-05 | Inform everyone of their work responsibilities at the face-to-face meeting and clarify the communication of the content of the meeting. | Expected to be a wake-up call for everyone | Open
Requirements | unclear requirements
scope creep
| constant requirements changes | For security reasons, we need to transform the database | 5 | 5 | 1 | 4*2*5=40 | Requirement Leader | 2023-09-29 | Change in the specific development process | Development changes | Open
Management | improper task assignments
improper planning
lack of management skills
Technology competence | Not familiar with the framework used
Not familiar with the programming language used
Not familiar with unit testing
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design
improper technology stack
Messy code
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment