## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/14-9/28 | Decided on tech stacks for different team members. Decision to change the database from MongoDB to Mysql. Set roles and responsibilities for the team members. Settled on a group and project name. | MongoDB is not suitable for the project due to safety concerns with monetary transactions | Assigning roles and responsibilities to team members. Deciding on project and group names. Planning for presentations. | At least one meeting per week. A team leader should prepare a basic agenda for the meeting and members should rotate as minutes takers. Change in database choice for better security. | 2 | 8 | 6 | 5 | 4 | 94 | 64 | 8 | 11 | 34 | 8 | 8 | 3 | 6 | 2
1 | 9/28-10/19 | * Prepared and discussed an upcoming presentation for iteration 1. Key assignments were made related to the presentation draft, PPT, Web Crawler, Framework, UI Design, and various documentation. Deadlines were set for various tasks. * Database updates were discussed with specific insights from Haoran & Xiaocheng. A presentation on the first version of UI pages by Huanzhou & Qinchen. Team feedback and suggestions on UI Design were noted. * Tasks were assigned for database design, UI pages design using Axure RP, resource gathering using website crawlers, and weekly report writing. * Technical stacks were discussed, and individuals were allocated specific stacks to learn and implement. There was a decision to change the database from MongoDB to MySQL. The homepage was set as the priority site to finish. | * No specific technical issues highlighted in one of the meetings. * Challenges related to database integration were discussed. Feedback and suggestions on UI Design were noted, indicating potential technical improvements needed. * The design of the database and the allocation of work related to it were discussed. * MongoDB was deemed unsuitable for the project due to concerns about its safety with money matters. A decision was made to switch to MySQL. | Discussions on preparing for the upcoming presentation, reviewing the progress for iteration 1, and setting deadlines for paperwork. Feedback sessions on UI design to understand the team's views and suggestions. The main focus was on task assignments and setting a deadline for task completion. Discussions around which tech stacks each individual should learn. | A clear allocation of tasks and responsibilities for different members was made. A deadline was set for paperwork, emphasizing the importance of being prepared ahead of the presentation. After feedback on the UI design, a decision was made to finalize UI changes, signaling the team's iterative approach to product development. Given the discussions on work allocation, the team can benefit from a centralized task tracking system (if not already in place) to monitor progress. The decision to switch the database from MongoDB to MySQL based on the project's needs signifies a willingness to pivot for better results. | 5 | 10 | 3 | 4 | 1 | 188 | 159 | 16 | 39 | 68 | 22 | 17.5 | 21.5 | 17 | 7
2 | 10/19-11/9 | User Stories/Tasks Completed: Deployment of an open-source framework, with specific focus on Vue.js for the frontend development. Implementation of unit testing to ensure software quality. Progress in Continuous Integration (CI) via GitHub Actions for efficient and automated integration processes. Big Progress: Transition from React to Vue.js for the frontend, optimizing the framework to better suit the project's scale and complexity. Developed mobile end using Swift. Significant headway in developing the software documentation, particularly the Software Test Documentation (STD) and Software Project Management Plan (SPPP). Good Practices Used: Regular updating of the Pivotal Tracker to maintain a clear record of the project's progress. Enforcing a policy requiring each team member to make multiple commits to the project repository, ensuring continuous contribution and progress tracking. Collaborative problem-solving in deployment issues, particularly in troubleshooting technical problems faced by individual team members. | Deployment Challenges: Difficulties faced by team members (Sai and Xiaocheng) in deploying the necessary technologies like Vue, Node.js, Spring Boot, Navicat, MySQL, MongoDB. Version Compatibility Issues: Encountering errors related to zookeeper and JDK, Node.js, and Maven versions, indicating a need for version compatibility checks and standardization. Framework Transition: Decision to switch from React to Vue.js for frontend development, requiring adaptation and learning of a new framework by the team members. | Team Collaboration and Coordination: Need for enhanced collaboration and assistance among team members in handling deployment challenges and learning new technologies. Task Delegation and Time Management: Effective delegation of tasks amongst team members, though continuous monitoring and adjustment might be required to ensure balanced workload and meeting deadlines. | Standardization of Tools and Versions: To avoid compatibility issues, standardize the versions of all tools and technologies used across the team. Enhanced Collaboration Tools: Utilize more collaborative tools for real-time problem solving and knowledge sharing, such as pair programming sessions or shared coding platforms. Regular Review and Adaptation of Strategies: Instituting regular review meetings to assess the progress of the project and adapt strategies as necessary, ensuring alignment with project goals and timelines. Focus on Documentation and Knowledge Transfer: Continuously update project documentation to reflect current progress and decisions, ensuring clarity and ease of onboarding for new team members or for future reference. Risk Management and Mitigation Strategies: Develop a clear risk management plan, identifying potential project risks (both technical and non-technical) and outlining mitigation strategies to proactively address these challenges. | 6 | 14 | 8 | 4 | 2 | 235 | 231.5 | 23.5 | 52 | 37 | 6.5 | 10 | 15.5 | 8 | 10.5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Bhargav Gundapaneni |  |  | Worked on the SDD Document

## Haoran Dai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Project Leader & Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 5 | 3 | 2 | 0 - Review the git 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 2 | 1 |  |  | 0.5 | 1 | 0.5 | 1. Write the readme 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Group member not farmiliar with git, and I need to teach him 2. communication is not clear. Task assignments is not clear. | 1. teach Yibo about the git basic operations 2. Ask everyone if they still had any question | 0 - Make the slides for the presentation 1 - continue to define requirements 3 - do some research about the tech stacks | 6
2 | 9/21-9/28 | 10 | 8 | 2 | 0 - Learn about some basic knowledge about Network 1 - define high level requirements 3 - make project slides, send reminders to team members, check the draft for the presentation 6 - set up MongoDB 7 - research similar products, prepare presentation, write the RiskManagement document | 1 | 0.5 |  | 5 |  |  | 1 | 0.5 | 1. Make the slides 2. Organize meetings twice a week to ensure the progress of everyone's work. 3. Participate in Iteration 0 presentation 4. Decide to change the database | 1. Group member are not very concern about the draft for the presentation 2. communication is not clear. Task assignments is not clear. | 1. Everyone is required to write the part they are responsible for. The specific part of the speech can not be written, but others must write it. 2. I will emphasize to everyone at the next in person meeting. | 0 - Learn about Java Web basic 1 - continue to define requirements 3 - do some research about the tech stacks | 16
3 | 09/28-10/05 | 10 | 8.5 | 1.5 | 0 - learn JavaWeb 1- make sure the website we are going to get data from 3 - create the database tables 5 - communicate about workload with team members 6 - reinstall the mysql 7 - Write the meetingminutes | 4 | 0.5 |  | 3 |  | 1 | 1 | 0.5 | 1. Design and create the database tables 2. Select the front end team and back end team | 1. Not familiar with Spring 2. Hard to choose where to start coding | 1.Finish JavaWeb and Spring tutorial in 3 weeks and know how to build backend coding 2.Start from the database implementation and login pages | 0 - Continue learning JavaWeb and Spring 3 - finish the web crawler 5 - Remind and ask teammates about the project | 10
4 | 10/05-10/12 | 19 | 18 | 1 | 0 - learn JavaWeb, Spring IOC 3 - implement web crawler 4 - Use the web crawler to test on some single product pages 5 - communicate with teammates about logo and page UI design | 6 |  |  | 9 | 3 | 1 |  |  | 1.Finish implementation of web crawler 2.Finish implement of the design of pages above and cart page, and part of home page 3.Discuss with teammates about workload and their | 1.Not got enough knowledge for react, so all the pages implement in this week only have basic interaction and cannot connect with backend yet 2.Not so familiar with UI design tools, so took too much time on some of UI effect implement | 1.Finish Sping tutorial in 2 weeks 2.Prepare for the presentation 3.Communicate with teammates about contents about presentation, and document works | 0 - learn JavaScript, React 5 - communicate about contents about presentation 7 - prepare presentation | 10
5 | 10/12-10/19 | 15 | 12 | 3 | 0 - learn Spring 3 - make project slides, send reminders to team members 3 - Finish the Web crawler work 3 - Get information about the system management system 5 - communicate about contents about presentation, assign different parts to everyone 7 - Update the readme.md | 2 |  |  | 9.5 |  | 3 |  | 0.5 | 1.Communicate with teammates about presentation contents 2.Prepare for the presentation 1 3. Finish the web crawler | 1.We need to find a way to store data to MySQL efficiently. 2.Still not got enough back-end knowledge, need to improve the learning speed 3.Need to get more communication with teammates. | 1.Transfer the data into msyql tables 2. Connect the Login and the user table of the project database 3. Develop the management system for the mall 4. Increase the frequency of communication with team members, actively contact, and use a variety of ways, including phone calls, text messages, etc | 0 - learn Springboot 3 - implement login and register system 3 - Transfer the data into mysql 3 - Work on the management system | 18
6 | 10/19-10/26 | 10 | 10 | 0 | 0 - learn Spring 3 - start writing the code 5 - Redesign the system, decide cut some modules | 2 |  |  | 6 |  | 1 |  |  | 1. Framework Build 2. New architecture for the project 3. New item for RiskManagement document | 1. Everyone doesn't care enough about the project. 2. Kang doesn't feel good, and need to have rest. | Increase the frequency of occurrence in the group so that more team members can see the work that needs to be done on this project | 0 - learn Springboot 3 - Write the tm-post module 5 - Have meeting with the group and assign everyone tasks | 18
7 | 10/26-11/2 | 16 | 12 | 4 | 0 - learn Spring 3 - Write the Backend Code - tm-Common 5 - Have meeting with the group, and help everyone to deploy the framework | 4 |  |  | 9 |  | 3 |  |  | 1. Runable Framework(Backend and Frontend) 2. tm-common code and part of tm-post 3. The division of work for everyone in Pivotal Tracker | 1. Everyone doesn't care enough about the project. Nobody starts the work 2. Sai feels bad. He took a lot of medicine and needed a lot of sleep. | Increase the frequency of occurrence in the group so that more team members can see the work that needs to be done on this project | 0 - learn Springboot 3 - Finish the tm-post 4 - Start Unit Tests 5 - Ask everyone to work for the iteration and every document | 20
8 | 11/2-11/9 | 25 | 23.5 | 1.5 | 0 - learn Spring 3 - make presentation slides, draft 3 - Implement the backend code (tm-post module) 4 - Unit Test for Post, User and Label 4 - Postman Setting, for the test next step 5 - communicate about contents about presentation, assign different parts to everyone 7 - Completion of Lab3 | 3 |  |  | 12.5 | 3 | 2 |  | 3 | 1. Backend code - tm-common and tm-post 2. Meeting Minutes Document 3. STD document 4. SPPP Riskmanagement Document 5. Presentation Slides 6. Presentation Draft for backend part 7. Lab3 8. Postman Team Creation and Set | 1. Everyone doesn't care enough about the project. Everybody just start work before the presentation, or not start 2. Sai still felt bad and ate a lot of paim pills. | Increase the frequency of occurrence in the group so that more team members can see the work that needs to be done on this project | 0 - learn Springboot 3 - Implement of User and Rest Modules 4 - Do more unit tests 5 - Communicate with QA leader, make sure the test plan | 20
9 | 11/10-11/16

## Bhargav Gundapaneni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 6 | 4 | 2 | 0 - learnt the github Agile 1 - modules required for the project, 5 - communicated through inperson and zoom 6 - set the git & github account | 2 | 2 | 1 |  |  | 1 | 1 | 0.5 | 1. git setup,and commit the message andd connected to VScode 2. Prepapred a slides for the Iteration 0 presentation | unable to decide which database to use regarding functuonal modules have to work on more regarding the functional modules | planned to work on functional modules and work on learning the spring boot and take look on some spring boot projects | 0 - work on slides for presentation 1 - identify requirements work on functional modules | 7
2 | 9/21-9/28 | 10 | 8 | 2 | 0 - Learning about Spring and regarding some implemtation steps 1 - worked on modulees functional 3 - functional modules expected one worked what 5 - communicated through inperson and zoomkind od functions we need 7 - work on slides | 2 | 1 |  | 5 |  | 1 |  | 1 | 1. worked on functional modules slides preparation 3. Presention on functional modules 4. Discussed regarding functional module which one to work on more | 1. need to arrange more inpperson meetings | Planning to not to work much on implemting the on payments due to payments issues and security and planned accordingly what are rewiref for the project will focus on those modules more instead of focusing on all of them | 0 - have to work on the implemtation and learning spring based projects 3 - work on implemation of dunctional modules accordingly | 14
3 | 9/28-10/5 | 12 | 10 | 2 | 0 - Learning: Database Design and Software Design Refreshing knowledge about Spring Boot fundamentals. Going through Spring Security documentation and authentication flow. 1 - Requirement Analysis: Gathering detailed requirements. Identifying any additional features required. Determining the structure of the database 2 - Design: Designing the database schema for user management. Designing the flow of the application (UML diagrams, flowcharts 3 - Implementation: Setting up the basic Spring Boot application. Creating entities and their relationships. | 4 | 5 | 6 | 4 |  |  |  |  | 1. worked on Userfields for Usermanaemnt, 2 1. worked on functional modules slides preparation2, worked on installing and setiing up IDES and worked on the Userfields which are mandatoey andd created a documented 3. worked on setting up environment for spring boot projects with sts4 4. created simple springboot project for usermanagementProject Initialization: Initial Spring Boot project setup. Dependency inclusions for JPA and security. Database Design & Configuration: Design and creation of the User entity. Repository interfaces for the entities. Database configurations in application.properties. Service Layer: Draft implementation of the UserService class. | Spring is hard to understand have to work on more projects to get efficient with spring hard tp set up the ennviroments and especially for springboot projects | Sucussfully installed the environment for spring boot projects and runned simple spring projects in sts4 and intellij checked wheather its running or not in the localhost enviroment before starting of implentation of the usermanagement | have to learn more about the springboot projectsImplement Spring Security for registration. Implement the core logic for the user registration process. Establish error handling mechanisms. | 15
4 | 10/06-10/12 | 21 | 20 | 1 | 0- spring web, Jpa. 3 - Implementation: Implementing the service layer, repository layer, and controllers. Setting up Spring Security for authentication 6 - Configuration/Environment: Setting up database configurations.Any other environment-related setups like properties files, profiles. 7 - Unclassified: Addressing any ad-hoc requirements. General bug fixes and improvements. | 3 |  |  | 8 |  |  | 6 | 3 | Deliverables: Service Layer Expansion: Full implementation of the UserService class. Password encoding and validation mechanisms for unique emails and matching passwords. Spring Security: Initial setup for Spring Security for registration. Custom security configurations for our registration needs. Error Handling: Exception handling mechanisms for common issues like duplicate email entries. | Challenges setting up the initial dependencies. Database connection issues during the initial setup | Completed the basic Spring Boot setup. Completed the primary database design. Partial completion of the service layer. | Improve error handling based on edge cases. Work on the user authentication mechanism using Spring Security. Begin the design of features for user account management. | 15
5 | 10/13-10/19 | 23 | 22 | 1 | 0- learening Spring Security Jpa 3 - Implementation Creating the registration and login UI using Thymeleaf templates. Handling form validations and feedback messages. 5 - Communication/Management: Discussing identified errors with the team. Prioritizing the errors based on severity and impact. 3 - Implementation : Begin fixing the high-priority errors. Ensure that the fixes for these errors don’t introduce new issues. Perform mini test-cycles post fixin | 2 |  |  | 18 |  | 2 |  |  | Deliverables: Refined Error Handling: Addressing and improving upon any error handling from previous weeks. User Authentication: Implement the login and authentication feature using Spring Security. Handle successful and unsuccessful authentication attempts. User Management (Backend): Design backend mechanisms for handling user profile view and management. | Difficulties in setting up Spring Security configurations. Data validation errors during the registration process. | Completed the user registration backend process. Initialized Spring Security with basic configurations. Implemented the initial error handling mechanisms. | Implement user profile management features in detail. Implement mechanisms to edit, update, and delete user profiles. Enhance security measures and refine authentication processes. | 20

## Huanzhou Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:Design Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/14-9/21 | 8 | 6.5 | 1.5 | 0: Initial research on React's capabilities, installing necessary libraries and tools. Dive into MongoDB basics. 1: Preliminary requirement analysis for the project based on the chosen tech stacks. 5: First team meeting to outline project objectives, set up communication channels. 6: Set up the development environment for React and MongoDB. 7: Scour online forums and documentation for potential challenges and pitfalls. | 3 | 2 |  |  |  | 1.5 | 1 | 0.5 | 1. Basic understanding of React and MongoDB. 2. Defined project requirements. 3. Setup of the initial development environment. | 1. Difficulty in understanding certain React functionalities. 2. Setting up MongoDB was more time-consuming than expected. | 1. Focus more on understanding React libraries and components. 2. Schedule a dedicated time to troubleshoot MongoDB setup issues. | 0: Dive deeper into React functionalities. 1: Finalize database schema for MongoDB. 2: Begin design phase for project architecture. | 8
2 | 9/21-9/28 | 10 | 8 | 2 | 0: Advanced React tutorials, understanding state management. 2: Design frontend components using React and outline how MongoDB will serve data. 3: Start implementing basic CRUD operations using MongoDB. 5: Regular check-in meetings, discussing challenges faced. 6: Modify development environment based on project progression. 7: Consult online communities for specific challenges faced during implementation. | 3.5 |  | 3 | 1.5 |  | 1 | 0.5 | 0.5 | 1. Initial frontend components designed. 2. Established connection between React and MongoDB, demonstrating basic data display. 3. Addressed and rectified some of the initial issues from week 1. | 1. Challenges in designing a responsive frontend. 2. Encountered data retrieval issues from MongoDB. | 1. Explore more React libraries for responsive design. 2. Research more on MongoDB best practices for data retrieval. | 2: Continue refining frontend design. 3: Introduce more complex operations using MongoDB. 4: Start testing the current functionalities. | 10
3 | 09/28-10/05 | 12 | 10 | 2 | 0: React learning 2: Design mall home page and cart page using Sketch and Figma. 5: Communication with teammates about the project. 7: Online resources for design. | 4 |  | 3.5 |  |  | 2 |  | 0.5 | Advanced React. Mall designs | React design challenges. Design iterations for the mall home page and cart page using Sketch and Figma. | Consulted React documentation and sought feedback on initial designs. Delved deeper into advanced React features. | Diving deeper into React functionalities. Modifying and refining designs based on feedback. Start the implementation of the mall home page and cart page. | 10
4 | 10/05-10/12 | 15 | 12.5 | 2.5 | 0: Continuous React learning. 2: Design modifications. New page designs. 5: Check-ins for design changes. 7: Online communities for React and design tips. | 4.5 |  | 4.5 |  |  | 2 |  | 1 | Enhanced React. More designs, including the Product Info page, Search List page, and Category page. | State management in React became increasingly complex. Ensuring design consistency across the pages designed and modified. | Leveraged React's state management tools to address challenges. Worked on achieving a uniform design across all pages. | Further advancement in React, exploring even more complex features. Begin creating backend logic for managing products and user interactions. | 12
5 | 10/12-10/19 | 10 | 8.5 | 1.5 | 0: Continued React study. 5: Communication with teammates. 7: Online platforms for troubleshooting and advice. | 3.5 |  |  |  |  | 2 |  | 0.5 | Deep insights into React. Strong management with teammates regarding the project. | Difficulties in choosing the best React libraries for specific functionalities. Overlapping tasks and responsibilities with teammates. | Held detailed discussions with teammates to streamline tasks and responsibilities. Established structured communication protocols to ensure smooth progress. | Continuation of advanced React functionalities, with a focus on integrating the frontend with the backend. Ensure seamless data flow and user experience. | 6
6 | 10/19-10/26 | 14 | 13 | 1 | 0: VUE learning 3: Setting up and configuring Vue.js environment for the project. 5: Team meetings to discuss transition from React to Vue.js and upcoming iteration planning. 7: Researching Vue.js best practices and solutions for potential issues. | 4 |  |  | 3 |  | 2 |  | 1 | Completed migration to Vue.js for front-end development; established a stable development environment for the upcoming iteration. | Adapting to Vue.js from React, initial setup issues with Vue.js environment. | Continued enhancement of Vue.js skills, resolution of setup issues, and ensuring a stable development environment. | Further Vue.js learning and practice, starting the design of the new front-end using Vue.js, beginning basic implementation in Vue.js. | 10
7 | 10/26-11/2 | 19 | 15 | 4 | 0 - JavaScript and Vue Learning 2 - configure and design API of front end 3 - More user stories and manul report cases 5 - communication about changing front-end framework, change project scope | 5 |  | 4 | 2 |  | 3 |  |  | Advanced proficiency in JavaScript and Vue.js; designed API for the front-end; prepared detailed user stories and manual cases. | Complexity in API design and integration, challenges in adjusting project scope to the new framework. | Focus on refining API design, continue adjusting the project plan to the new scope. | Continue JavaScript and Vue.js mastery, finalize API and start frontend integration, develop and refine user stories and manual report cases. | 14
8 | 11/2-11/9 | 22.5 | 20 | 1.5 | 0 - learn VUE, Swift 2 - Design logic and UI pages of mobile end on iOS 3 - Implement the mobile end code using Swift 4 - Conducting unit tests with XCUITest. 5 - Regular communication with team members on progress and challenges. 7 - Completion of Lab3 | 3 |  | 3 | 6 | 2 | 3 |  | 1 | designed and implemented UI and logic for mobile app, conducted successful unit tests. | Challenges in Swift implementation, issues in UI design consistency for the mobile app. | Further Swift learning and practice, address UI design issues and ensure consistency. | Deepen skills in Vue.js and Swift, continue development and enhancement of the mobile app, start integration testing of mobile functionalities. | 18

## Qinchen Gu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Q&A Leader & Front-end developer
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 7 | 6 | 1 | 0 - learn git, html, css 1 - define high level requirements 5 - communicate with teammembers, get to know each other 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 |  |  |  | 1 | 1 | 0.5 | 1.Get to know each other 2.Divide the work and take charge of front-end 3.Set up git | 1. Know nothing about html, css, javascript and react 2. Not so good in communication with teammates and not divide roles yet | 1.Start front-end stack tutorials, start from html and css, and finish it in a week | 0 - Continue learning React and JavaScript 5 - Continue communication with teammates about project 7 - prepare presentation | 6
2 | 09/21-09/28 | 8 | 6 | 2 | 0 - learn html, css, JavaScript 5 - communicate about roles, presentation and project needs 7 - prepare presentation | 3 |  |  |  |  | 1 |  | 2 | 1.Decide I should speech about tech stacks 2.Finish part of pre draft, especially for myself and Huanzhou 3.Take charge of Q&A leader | 1. Not got enough knowledge for front-end develop | 1.Continue html, css tutorials and start JavaScript tutorials 2.Finish pre draft and ready for pre | 0 - Continue learning React and JavaScript 5 - Continue communication with teammates about project | 6
3 | 09/28-10/05 | 5.5 | 4.5 | 1 | 0 - learn JavaScript, React 2 - design where to start project and design home page 5 - communicate about project needs and where to start | 3 |  | 1 |  |  | 0.5 |  |  | 1.Finish a part of MeetingMinutes 2.Discuss with teammates about database stack change | 1.Still not got enough knowledge for react 2.Don't know where to start our first page | 1.Finish React tutorial in 2 weeks and know how to build websites 2.start the project making and finish home page | 0 - Continue learning React and JavaScript 3 - finish first page-homepage 5 - Continue communication with teammates about project | 6
4 | 10/05-10/12 | 19 | 18 | 1 | 0 - learn JavaScript, React 2 - design login, register and related pages 3 - implement login, register and related pages 3 - implement cart page and background 4 - test all the connections between current pages 5 - communicate with teammates about logo and copyright | 1 |  | 4 | 12 | 1 | 1 |  |  | 1.Finish design of login, register and related pages 2.Finish implement of the design of pages above and cart page, and part of home page 3.Discuss with teammates about change a logo to get rid of copyright issue | 1.Not got enough knowledge for react, so all the pages implement in this week only have basic interaction and cannot connect with backend yet 2.Not so familiar with UI design tools, so took too much time on some of UI effect implement | 1.Finish React tutorial in 2 weeks 2.Prepare for the presentation 3.Communicate with teammates about contents about presentation, and about future works in our project | 0 - learn JavaScript, React 5 - communicate about contents about presentation 7 - prepare presentation | 6
5 | 10/12-10/19 | 13 | 12 | 1 | 0 - learn JavaScript, React 3 - implement login, register and related pages 3 - implement cart page and background 5 - communicate about contents about presentation 7 - prepare presentation | 2 |  |  | 8 |  | 1 |  | 2 | 1.Communicate with teammates about presentation contents 2.Prepare for the UI design and implement part of presentation | 1.Not pay enough time on project this week, but that's because I will have midterm for other courses this week 2.Still not got enough front-end knowledge, all the work are studying while implementing, that make efficiency quite low | 1.Finish React tutorial in 1 week 2.Implement category page, search list page, product info page 3.design more pages needed 4.Implement login and register system to connect with back-end and database | 0 - learn JavaScript, React 2 - design other pages needed 3 - implement of category page, search list page, product info page 3 - implement login and register system, and start other coding jobs | 6
6 | 10/19-10/26 | 16 | 15 | 1 | 0 - learn JavaScript, React 3 - implement product info page 3 - implement user profile page 3 - implement search list page 5 - communicate about future works | 3 |  |  | 12 |  | 1 |  |  | 1.Communicate with teammates about future works 2.implement of product info page and user profile page 3.Write test part of SPPP document | 1. Able to write code with React but still not so familier, need more study and more practice 2. No idea what page to do in the coming week 3. Not so familiar with connection between frontend and backend | 1. Find more React tutorials and try to learn more 2. Learn some knowledge about API and find some ways about how to do the connection, for example ajax | 0 - learn JavaScript, React, API 2,3 - design and implement more pages 3 - start coding for API, get ready for connection between front and back | 6
7 | 10/26-11/2 | 24 | 20 | 4 | 0 - learn JavaScript, Vue, Ajax 2 - design "home page", login panel, register panel, category(label) page for our new forum-like mall 2 - design API of front end 3 - implement new "home page", login panel, register panel, category(label) page 5 - communicate about changing front-end framework, change project scope 7 - help teammates deploy templete of new project scope, and help them study from templete | 4 |  | 2 | 14 |  | 1 |  | 3 | 1.Communicate with teammates about changing project scope 2.Design and implement pages for our peoject under new scope 3.Design API for frontend and ready for implement 4.Help teammates find a templete for new project scope, and help team members deploy and study from the templete and ready for new page design and implement | 1. Don't got enough time since the change of scope is in a sudden 2. Pages are not so good looking since I am not a good designer and willing to finish more pages 3. Didn't finish API implement, didn't communicate with teammates of backend for API connection | 1. Find some Vue tutorials and try to learn deeper of it 2. Finish API implement and test connection with backend 3. Learn about unit tests about front-end | 0 - learn JavaScript, Vue, Ajax, Unit test 2,3 - design and implement search list, post page 3 - implement API and try connection 5 - communicate about API connection details 7 - Prepare for presentation | 6
8 | 11/2-11/9 | 24 | 23 | 1 | 0 - learn JavaScript, Vue, Axios(Ajax), Jest(Unit test), e2e(Unit test) 2 - design for manage part of project(front end) 3 - implement API, search list, Post page 5 - communicate about API connection details, presentation details 7 - Find some materials for pages 7 - Prepared for frontend part of presentation | 6 |  | 3 | 10 |  | 1 |  | 4 | 1.Finish API front end part 2.Finish STD doucment part 2,3,4 3.Double check SPPP test related parts | 1. Pages are not so good looking 2. Frontend and backend can not successfully connect, need more fix 3. Some pages and some functions recently have are not so suitable, need some changes 4. There are many bugs in the program 5. Need more study of unit tests | 1. Learn more about API, Vue, Unit test 2. Design and Implement more pages needed 3. Design and try to use some unit tests 4. Discover more possibilities about API and try connect with backend 5. change CSS format and materials if time is available | 0 - learn JS, Vue, Axios, Jest, e2e 2,3 - Design and implement more pages(manage and so on) 4 - design and implement some unit tests 4 - do more attempt about API and front-back connect | 6

## Xiaocheng Kang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement & Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn with teammates about what to do 1 - define what I need to do with project 5 - make project plans 6 - setup git | 2 | 1 |  |  |  | 1 | 1 |  | setup github, doing commiting and lab1 | Forget how to done git firstly, it takes some time to retrive. | Finishing learning how to do git things | 0 - continue lerning what we should do 1 - continue finding which part I need to complete 5 - make more details for project plan | 6
2 | 09/21-09/28 | 8 | 7 | 1 | 0 - learn back what to do a website 1 - Make sure what we want to display, and what others want 5 - Project Plan completed 6 - setup Visual Studio for me to write codes 7 - Prepare the presentation for iteration 0 | 5 | 1 |  |  |  | 0.5 | 0.5 | 1 | 1. Complete the SPPP document 2. Prepare the project 3. Meeting to do the presentation slides 4. Participate in Iteration 0 presentation | 1. Not very sure the SPPP file is a great completion 2. Stuck on which DB we should use | 1. Finishing the tutorial of Web Design, should be able to complete a templete website. 2. Received tasks from team leader, let me know what I should do for next | 0 - learn more about Web Design things 1 - Using learned knowledge to create a web template 2 - Design a templete 4 - Test if the web running correct 5 - meeting to find out if it is possible | 7
3 | 09/28-10/05 | 8 | 7 | 1 | 0 - learn how to do web crawling, and learn to do web 1 - Make sure the web which we wanna do the crawl 5 - Allocate the database design, and do the UI pages 6 - Visual Studio and excel for the crawling | 4 | 1 |  |  |  | 2.5 | 0.5 |  | 1. Figure out Lab2 2. Prepare to do the web crawling 3. Meetings to talk with each other about following steps | 1. Not familiar with web crawling 2. Hard to figure out the SPPP file | 1. Finishing tutorial about web crawling 2. Reveived tasks from teammates, figure them out | 0 - learn more about Web Crawling 1 - Try to do web crawling 2 - Help to design UI pages 4 - Testing 5 - meeting to find out the problems | 8
4 | 10/05-10/12 | 14 | 13 | 1 | 0 - learn more about web crawling 1 - Make sure the things which we crawled can be used 2 - Web Crawling 5 - Decided the deadline for our next version | 3 | 1 | 8 |  |  | 1 |  |  | 1. Complete Quiz 1 2. Continue doing web crawling 3. Meeting to assign tasks for each other | Not doing well with web crawling, asking friends for help | 1. Learn more web crawling things, ask more and receive more details 2. Prepare for presentation 2 | 0 - Continue learning Web Crawling 1 - Design more to make it great 2 - Continue doing web crawling 4 - Testing 5 - let teammates know what's going on 7 - Presentation 2 | 15
5 | 10/12-10/19 | 13 | 12 | 1 | 0 - Continue learning about web crawling 2 - Web Crawling 7 - Prepare the presentation for iteration 1 | 4 |  | 6 |  |  |  |  | 2 | 1. Update SPPP document 2. Continue working web crawling 3. Prepare for presentation | Found that it is a little bit complex for completing SPPP document, talk with teammates and try to figure it out | 1. Learn more web crawling if needed 2. Help with web design | 0 - Continue learning Web Crawling if needed 1 - Do some Web design 4 - Testing 5 - meeting to find out what to do next | 15
6 | 10/19-10/26 | 12 | 11 | 1 | 0 - Learn how to deploy sending by Haoran 1 - Try to deploy 5 - Talk with teammates to know what to do | 8 | 2 |  |  |  | 1 |  |  | 1. Check what else can be done 2. Continue learning how to deploy | There are lot of errors when I first deploying the environment. Trying to figure it out by searching on Internet, and ask teammates. | 1. Check the file which Haoran sent to us 2. Doing more on code | 0 - Continue learning to deploy 1 - Successfully deploying 2 - Coding more after deploying 5 - Ask more if I have questions | 20
7 | 10/26-11/2 | 17 | 16 | 1 | 0 - Continue learning how to deploy 1 - Deploying the environment 4 - Test if my deploy is successful 5 - Ask teammates to help me deploy | 7 | 3 |  |  | 1 | 5 |  |  | 1. Change some part of SPPP file 2. Deploying with Haoran and Qinchen's help 3. Failed to deploy because of zookeeper 4. Trying to figure that out | During this week, Haoran and Qinchen helped me to make the deploy, however, we found an error called zookeeper, but we cannot find what to do at that time. Good news is it can be deploy on Haoran and Qinchen's laptop. | 1. Figure out what zookeeper error is. 2. Complete the deploying 3. Complete the tasks which assigned to me | 0 - Learn how to do Github Actions 2 - Make some CI to run 4 - Test if CI can run succuessfully 5 - Communicate with teammates 7 - Prepare for Pre2 | 20
8 | 11/2-11/9 | 15 | 14 | 1 | 0 - Learn how to do Github Action (CI) 2 - Design CI for our Github 4 - Test if the CI is good for us 5 - Tell teammates what I have done 7 - Prepare the Presentation 2 | 6 |  | 3 |  | 2 | 1 |  | 2 | 1. Figure out what CI is, and learned how it runs 2. Write a CI yml file, called Check Java Version 3. Ask teammates to help testing 4. Write it into our presentation | During this week, I learned from Github and website to know how to write a CI, and how it works, after learning, I asked my teammates to help to test if it works or not. Good new is it works! | 1. Try more CI test 2. Help with Frontend teammates 3. Doing more codes | 0 - Learn Vue 1 - Doing some part of Vue 2 - Design our website 5 - Tell teammates what I have done | 20