## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | one member left our group | 1 | 3 | 4 | 4*2*5=40 | team leader and all members | N/A | Increase the workload of each person. Two people are responsible for front-end development, two people are responsible for back-end development, and one person is responsible for assistance. | No one dropped the class so far | Close
| Lack of motivation and responsibility | Lack of sufficient communication between team members | 5 | 5 | 5 | 1*1*5=5 | Team leader and all members | Nov 4. | Increase meetings and work together to improve everyone's efficiency. Assign fewer tasks to each time to make everyone's work clearer. |  | Open
| Xiaocheng got sick | Xiaocheng got sick and need rest | 5 | 2 | 5 | 1*4*5=5 | Xiaocheng | 2023-10-16 | Qinchen took his work |  | Close
| Sai got sick | Sai got sick and can't be contacted | 5 | 5 | 5 | 1*1*5=5 | Sai | 2023-11-07 | Other members of the back-end group will complete his work. | It may not be possible to complete many Unit Tests. | Open
| Huanzhou got sick | Huanzhou got sick | 5 | 2 | 5 | 1*4*5=5 | Huanzhou | 2023-11-08 |  |  | Open
Communication | duplicate work
worked on wrong components
| useless work | Spend too much time on UI design | 5 | 2 | 4 | 1*4*4=16 | Front End Group: Qinchen Gu, Huanzhou Wang and Xiaocheng Kang | Oct 20 | Start writing the code immediately. Because everyone is not familiar with React, it has been transferred to the Vue architecture with a lower learning curve for development. | At present, part of the coding has been completed, and more work needs to be continued. | Close
| inconsistent work | Because someone can't attend the meeting, the message of the meeting will not be clear enough. | 5 | 3 | 1 | 4*2*4=32 | team leader | 2023-10-05 | Inform everyone of their work responsibilities at the face-to-face meeting and clarify the communication of the content of the meeting. | Expected to be a wake-up call for everyone | Close
Requirements | unclear requirements
scope creep
| constant requirements changes | For security reasons, we need to transform the database | 5 | 5 | 1 | 4*2*5=40 | Requirement Leader | 2023-09-29 | Change in the specific development process | Development changes | Close
Management | improper task assignments
| improper planning | We didn't spend much time on code implementation before, and now we need to seize the time to implement the code. | 3 | 5 | 5 | 3*1*5=15 | All Group | 2023-12-10 | Implement the entire system by function |  | Open
| lack of management skills | Due to the lack of project experience and insufficient prediction of everyone's ability and responsibility, there are problems with the time allocation of the project. | 5 | 5 | 5 | 1*1*5=5 | Haoran Dai | 2023-11-07 | Increase everyone's ddls. If some people really can't get in touch or can't work, they can only inform the teacher of the situation. |  | Open
Technology competence | Not familiar with the framework used | Because there are many version requirements between different artifacts of the project, it will take a lot of time to adjust. | 3 | 3 | 3 | 3*3*3=27 | Haoran Dai |  | Refer to other people's projects to confirm which versions of the artifacts can work together. | Learn the importance of configuration for Spring | Close
| Not familiar with the programming language used | There's limitation for the version of node.js | 5 | 3 | 3 | 1*3*3=9 | Haoran Dai, Qinchen Gu | 2023-10-30 | At first, we didn't notice the version problem of Node.js, but because the switching of the device would lead to a working error of Node.js, we found this problem and set it according to the running version. | Learn the importance of the version control | Close
| Not familiar with unit testing | Currently doing as much Unit Testing as possible | 4 | 5 | 2 | 2*1*2=4 | Backend Group: Haoran Dai and Sai | 2023-11-08 | Implement the Unit Test for the Login and some other functions |  | Open
Other technology incompetence
| Not familiar with Git | There are problems updating the code | 5 | 3 | 3 | 1*3*3=9 | Haoran Dai | 11//7
Design and implementation | Improper design | In order to ensure that the poster's information is not leaked, bilateral identity verification is required before you can see the poster's information | 3 | 3 | 5 | 3*3*5=45 | Backend Group: Haoran Dai and Sai | 2023-11-15 | Realize the private chat system, or more strictly standardize the registration process |  | Open
| improper technology stack | From React transfer to Vue | 5 | 2 | 3 | 1*4*3=12 | Frontend Group: | 2023-12-10 | Implement the front end with Vue |  | Open
Messy code
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment